Value Statement

To ceaselessly strive at maximizing value for our customers by enabling the delivery of highest quality sales & marketing solutions at the lowest possible cost;  driven  by our customer focus, and our determination to work as a TEAM with our customers

Jay Jablonski

VP & GM IMS Division

SGT Inc

5433 Westheimer, Ste 1016

Houston, TX 77056

Sgtglobalresearch.com

jjablonski@sgtus.com

P: 520-390-2893

F 713-979-3975

Market Development Proposal

Submitted by

This Agreement (the “Agreement”) between COMPUMED having its principal place of business in Los Angeles Ca. and Symcon Global Technologies (SGT), a Texas corporation with an office at 5433 Westheimer, Suite 1016, Houston, Texas 77056 (the “Company”) is entered into for the purpose of engaging the marketing services and expertise of the Company in accordance with the terms and conditions contained herein.

- Introduction

COMPUMED is a nationally recognized leader in tele-monitoring bone imaging and EKG tests over broadband connections for rural or remote healthcare providers.

The purpose of this proposal is to put a sustainable program of lead qualification in place that identifies and rates the sales potential of the rural or remote health care providers that would improve services by providing patient care using the COMPUMED testing services. The goal would be to provide a group of ranked sales profiles measured by interest and revenue potential for follow-up by the COMPUMED staff.

SGT will assist in the design and will execute a blind survey program that will gather information on the way the selected clinics purchase testing services or and determine their ability and willingness to purchase these services from a provider like COMPUMED. Additionally the volume of tests required will also be established. Sgt will do this through a series of pre-approved questions. These surveys will provide COMPUMED with qualified sales profiles which will cut the time required for the COMPUMED sales team to reach the best new perspective clinics by as much as 80%. SGT will assist COMPUMED in constructing the survey and the scoring system. Usha Dasari PhD in market research and Jay Jablonski MA Marketing will assist in the design and execution of the program. SGT will assign an experienced Project Manager to execute this effort on a day to day basis.

All sales and marketing efforts require consistent effort over time to produce a real ROI on marketing expense. One shot “Blitz” programs are rarely successful. SGT is structuring the program under the assumption that it will be executed over the next 3.5 months. Using this approach will have the best effect for the following reasons:

- Resources improve on projects over time as they gain experience

- Consistent effort over a time will increase the percentage of prospects that become buyers

- This team can be easily scaled up should greater effort be required.

- Reporting and data collection will be superior over start and stop efforts.

- Background

SGT Global Research is a professional services company providing Marketing Support programs to its clients. SGT helps its clients gain a significant return on their marketing investments by providing a portfolio of marketing related services.  Programs include Market research and sales support services that have proven sales benefit for clients. The SGT Marketing Services division has 14 years of experience and has successfully provided marketing research and analytics projects for private and publicly traded firms across various verticals. Some of our marquee clients include American Express, Moody’s, Novell, Network Associates, Enersys; E-Gain; Sun Microsystems; Freeport McMoran, and a large variety of private companies. Please visit WWW.Sgtglobalresearch.com  for additional information.

- Scope of Work

COMPUMED would like to qualify a large pipeline of rural health care providers for its testing services. SGT proposes the following process to develop a qualified sales pipeline of the best candidates for expansion of the business.

PHASE 1: A working universe of targets about 2000 targets will be more than sufficient to maintain the program over a 90 day period. SGT and COMPUMED will work to develop this listing.

SGT and COMPUMED will work to qualify this universe into active sales targets. SGT will administer the survey to prospects that COMPUMED has identified as having the best job titles to provide accurate information. SGT will apply a sales qualification algorithm to the survey results in order to rate the companies with the best revenue potential. SGT will assist COMPUMED in setting up responses based on the lead quality and revenue potential. For example: a high scoring lead may be routed to sales staff for appointment setting, while lower scoring leads may receive a mailing or E-Mail solicitations.

SGT will work with COMPUMED to design a survey program that can be executed as a phone interview or answered by E-mail or Fax response so the sales target can answer the questions over the phone or at a later move convenient time for them. Please note that No Surveys will be released without a call first confirming the target as a person with responsibility for testing services at the target clinic.

Phase 2: SGT will execute the Surveys and provide weekly updates to COMPUMED. The goal of the project will be to develop a proprietary sales prospect database and a strong pipeline of new customers that will have fuel the expansion of remote testing services in 2009 and 2010. Follow-up contact programs will serve to convince this group of customers that COMPUMED provides the best tool for remote testing.

Process & Deliverable for execution of the Two Phases:

Phase 1 to be completed over 2 weeks total cost $1000

Process

SGT’s senior executives who have over 10 yrs of experience in organizing surveys and interpreting data will be engaged in structuring and creating the survey instrument. The survey will be structured so that it can be done over the phone, or at the request of the prospect E-mailed or faxed so that the respondent can answer the questions. Each survey will be designed so that each company can be rated in terms of sales potential by pinpointing information on areas that are of greatest significance to COMPUMED

.

Phase 2 to be completed over 90 Days Total Cost $18,000

Process

Using the surveys constructed during Phase 1, SGT will execute qualification surveys among the targets approved by COMPUMED. The survey will be directed at the people with responsibility for making decisions about providing care at the targeted remote clinics.  SGT will work with COMPUMED to use a survey scoring algorithm that will identify the best sales prospects for immediate sales pursuit by the COMPUMED sales team. SGT can follow-up and set up the sales appointments if required.

Deliverables

Individual Scored Survey results in excel format or the format of COMPUMED’s preference

Sales Appointments with qualified accounts

Monthly Itemized costs for phase 2

- Two full time survey specialists @ $15 per hour                                        2500x2    $5000

- Senior Research analyst project manager                                                                 $ 500

- Budget for time required to develop contact list                                                          $500

- Total Monthly Budget                                                                                                  $6000

- Expected Scope of Deliverables vs.  FTE Labor equivalent internally

- Research Database of over 2000 Targets with Executive Names and Contact Data

- Approximately 12,000 calls to attempt surveys

- Between 500 & 700 Completed sales profiles

- Estimate of 200 to 250 Leads requiring sales contacts

- Weekly meeting with project updates with Senor Research Analyst

- Professional constructed scored survey instrument Phone or Fax

- E-mail version with completed HTML Programming

- PhD level data analysis and recommendations for 2010 sales targeting

- This work above is Equivalent to One Year’s work for a college educated FTE with a sales and marketing background---------- between $3500-$4500 per month salary and benefit cost at current market rates. This suggests a $45,000 average cost if done internally by a competent full time employee over a year. SGT provides equivalent work in 3.5 months for $19,000

:

- Pricing and Terms

Consulting to create the survey instruments and scoring system:                             $1,000

Monthly Cost of Project Resources for 3 months                                                          $6,000

Total Project                                                                                                                       $19,000

| On Signing of contract | $1000 |
| --- | --- |
| End of month one | $6000 |
| End of Month two | $6000 |
| End of Month three | $6000 |
| Total | $19,000 |

Cancellation clause: Program may be canceled anytime with a termination fee of 50% of the unpaid balance.

- Agreement Page

Accepted and Agreed to by:

For SGT Inc					For COMPUMED

By:	Jay Jablonski                              By:   ___________________________

Title:	VP & GM IMS Division		Title: ___________________________

August 11, 2009                                      Date	___________________________